## Sheet1
	Module	Task Name	Hours	Dev Name	Status	Remarks
1	Fast API	Create an endpoint to receive user's request	0.5	Ronak	Pending	This will validate the incoming request with access token.
2	Fast API	Create a method & validate input JSON	0.5	Ronak	Pending	This will validate all data received in request JSON so that we don't endup with unknown error. If there is an error, fast api will return the response from here itself.
3	Fast API	Add LiteLLM library	0.5	Ronak	Pending	Add https://github.com/BerriAI/litellm library and related settings (like token name etc)
4	Fast API	Create Hugging face request object	0.5	Ronak	Pending	This will create request body for HF.
5	Fast API	Create Prompt	0.5	Abhay	Pending	This will be based on what kind of request is. We have to create multiple types of prompts to get accurage result.
6	Hugging Face	Create a new space & create gradio UI	1	Ronak	Pending	Using https://huggingface.co/docs/hub/spaces-sdks-gradio & UI mockup provided.
7	Hugging Face	Model invocation code	4	Abhay	Pending	Write python code to consume SalesForce CodeGen25 model so that we can invoke model by passing prompt generated above and receive an output.
8	Fast API	Invoke Fast API	1	Ronak	Pending	Invoke HF API developed by Abhay by using litellm library.
9	API Doc	Create Fast API Doc - Postman Collection	1	Ronak	Pending	For UI team to consume with sample input & output JSON
10	API Doc	Create HF Doc - Postman Collection	1	Abhay	Pending	For Python team to consume with sample input & output JSON
11